## Guidance
GUIDE TO COMPLETING THE SCHOOL ASSET MANAGEMENT PLAN
School Name: | Please enter School Name |  | Prepared by: | Date: (dd/mm/yyyy) | Date AMP was prepared | Page |  | of
School Number: | Please enter School Number |  | Person who prepared the AMP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Priority (High, Medium, Low) | What? | Where? (Main building, nursery block, etc) | Why? | When? (We are not able to fulfill all works during the school holiday's so please be as flexible with when the works could be done as possible please) | Benefits? - known & assumed | Known or Estimated cost £ (if unknown please state unknown) | Funding source(s) (inc brief breakdown if applicable) £ | School's Project Lead(s) | Comments
N.B. The cells where you input your AMP information will be coloured grey until you type some text into the cells.
1 | The Priority of the works, Low, Medium & High
2 | What, what are the works that are going to be carried out
3 | Where, where the works need to be carried out, if you have access to Technology Forge please enter the block number.
4 | Why, why do the works need to be carried out
5 | When, when could the works be carried out
6 | Benefits, what benefits would be realised if the works are carried out
7 | Known or Estimated Cost, the cost of any works and any fees if known.
8 | Funding Sources, where is the funding coming from?
9 | School Project Lead, the school's appointed person(s) who are responsible for the project. The person(s) should be resonsible, capable and have the agreed accountability to be able to carry out any duties assigned to them regarding the project.
10 | Comments, any additional information regarding the project.
11
| Approved by: |  | B Good |  |  | Sign: | B Good |  |  | Date: | 05/01/2011 | Appointment: | Head Teacher
| Approved by: |  | T Worke |  |  | Sign: | Terry Worke |  |  | Date: | 05/01/2011 | Appointment: | Chair of Governers
11. APPROVED BY. To be completed by responsible and accountable persons. Two signatures are required.

## Blank AMP
SCHOOL ASSET MANAGEMENT PLAN
School Name: |  |  | Prepared by: |  | Date: (dd/mm/yyyy) |  | Page |  | of
School Number:
Priority (High, Medium, Low) | What? | Where? (Main building, nursery block, etc) | Why? | If a boiler or electrics is it operational now? | When? (We are not able to fulfil all works during the school holiday's so please be as flexible with when the works could be done as possible please) | Benefits? - known & assumed | Known or Estimated cost £ (if unknown please state unknown) | Funding source(s) (inc brief breakdown if applicable) £ | School's Project Lead(s) | Comments
Approved by: |  |  | Sign: |  |  | Date: |  | Appointment:
Approved by: |  |  | Sign: |  |  | Date: |  | Appointment:

## Example AMP
SCHOOL ASSET MANAGEMENT PLAN (AMP)
School Name: | 999 |  | Prepared by: | Date: (dd/mm/yyyy) | 01/06/20xx | Page | 1 | of | 1
Mr Good
School Number: | A Primary
Priority (High, Medium, Low) | What? | Where? (Main building, nursery block, etc) | Why? | When? (We are not able to fulfill all works during the school holiday's so please be as flexible with when the works could be done as possible please) | Benefits? - known & assumed | Known or Estimated cost £ (if unknown please state unknown) | Funding source(s) (inc brief breakdown if applicable) £ | School's Project Lead(s) | Comments
High | Re-roof main school building. School condition data C2. | Main building (block 10) | Severe roof leaks are causing Health & Safety problems (slippery floors & electrical safety). Decoration, equipment & possible structural damage. Low energy efficiency. Children’s work damaged in three classrooms. | Plan for summer 2011 | Elimination of Health & Safety hazards. Improved staff and pupil morale. | £175,000 | AMP Central Budget with contribution from Devolved Formula Capital. | Mr Jones | Funding provisionally agreed. Tender for works. Summarise improvements & enter into SIP.
High | Liase with CSF and discuss requirement to build 2 new permanent classrooms with associated toilets and cloakrooms. | N/A | Pupil projections show that NOR will exceed capacity in 2013. | Before Sept 2013 | Existing high standards can be maintained. School will be able to accommodate larger NOR. | £250,000 estimated | LEA Central Funding secured via ‘Basic Need’ bid to DES. | Mrs Good | Further discussion with CSF to confirm requirement. Summarise improvements & enter into SIP.
High | Long term plan for replacement of 2 x boilers & update of associated controls. School condition data C3. | Main building (block 10) | Current LPH system is heated by 2 x boilers that were installed when the school was constructed (21 yrs old). Although still functioning spares and the like are no longer available. The boilers are poor in energy efficiency. | Before Winter (will work with contractors to agree mutually acceptable time) | More efficient heating system and lower heating costs. Reduces risk of breakdown & maintenance costs. Reduce carbon emmisions. | £85,000 | 2 x boilers cost £55,000. Seek funding. | Mr Jones | Tender for works. Summarise improvements & enter into SIP
Medium | Cramped and ageing front reception area. No disabled access. | Main building (block 10) | Remove partition wall between room G54 (existing reception class) and G55 (adjacent spare classroom) to create larger area. | TBC | Improve the initial look of the school. Enable for disabled access. | £20,000 estimated | Devolved Formula Capital School Budget | Mr Jones | Quotations required ASAP.
Low | Hall area at present is in need of redecoration and gives pupils/visitors an unattractive impression of the school. | Main building (block 10) | Renovate hall floor and ceiling, remove stage area and lighting system, redecorate hall and purchase new curtains. | Summer Holidays 2013 | Hall is used for music, PE and drama. More attractive surroundings will encourage more pride in work, increase standards and improve National Curriculum levels achieved. | £15,000 | School Maintenance Budget Devolved Formula Capital School/PTA Fund (curtains) | Mrs Good | All funding agreed. Work is scheduled to start at Easter break. Summarise improvements & enter into SIP.
Low | Build a large walk in cupboard off the cloakroom area and include shelving. | Main building (block 10) | Curriculum resources are currently stored in several small stores and not used frequently as inaccessible. | Summer Holidays 2013 | The school’s resources for curriculum areas will be centralised, suitably stored and readily accessible. Staff will have more awareness of resources available. | Unknown | Devolved Formula Capital | Mr Jones | Quotations required ASAP.
Approved by: |  |  | Sign: |  | Date: |  | Appointment:
Approved by: |  |  | Sign: |  | Date: |  | Appointment: